## Total
Option 1 - S3 API | Yes
Mandatory task | Total estimation man/days
No | 65
Yes | 47
Grand Total | 112
Option 2 - SAP MDT | Yes
Mandatory task | Total estimation man/days
No | 65
Yes | 107
Grand Total | 172
Option 3 - SAP PO | Yes
Mandatory task | Total estimation man/days
No | 65
Yes | 91
Grand Total | 156

## Estmation for EDI-storage
Option 1 - S3 API | Option 2 - SAP MDT | Option 3 - SAP PO | Mandatory | # | Task | Design | Build | Test | Cutover & Go-live | Comment 1 | Comment 2 | Comment 3
Yes | No | No | Yes | 1 | Data migration SAP EDI content data via S3 API (rclone) | 3 | 7 | 3 | 3 | Rclone is a command-line program to manage files on cloud storage. It will sync data between Selectel object storage and EDI-content server. Any other S3 (AWS-kind) client could suit. | https://rclone.org/ https://docs.selectel.ru/cloud/object-storage/tools/rclone/
No | Yes | Yes | Yes | 2 | Data migration SAP EDI content data via SAP interfaces | 3 | 10 | 3 | 5
Yes | Yes | Yes | Yes | 3 | ABAP program and interface 1 for mapping SAP ECC data - SAP EDI content (link between files and metadata) | 4 | 8 | 2 | 3 | Frequency - once per week or rarely (not real time) | Techincally could be implemented within one common interface - TBD/TBC on detailed design step
No | Yes | Yes | Yes | 4 | Interface 2 with SAP content server: send EDI content server data | 5 | 10 | 5 | 3 | Frequency - once per week or rarely (not real time) | Techincally could be implemented within one common interface - TBD/TBC on detailed design step
No | Yes | Yes | Yes | 5 | Interface 3 with SAP content server: send changes | 3 | 7 | 3 | 3 | Frequency - once per week or rarely (not real time) | Techincally could be implemented within one common interface - TBD/TBC on detailed design step
No | Yes | No | Yes | 6 | Create Apache NiFi pipeline to obtain EDI files data processing | 3 | 7 | 3 | 3 | Get data from SAP interfaces | SAP PO can send data directly to S3 storage via S3 API. In this case we may not use Apache NiFi. Assumtion: MDT doesn't have capability to use Selectel API. | https://developers.selectel.ru/docs/cloud-services/cloud-storage/
Yes | Yes | Yes | Yes | 7 | S3 object storage configuration | 2 | 7 | 2 | 1
Yes | Yes | Yes | Yes | 8 | S3 object storage sizing estimation | 2 |  |  |  | Actual year - standard storage, previous years - cold storage | https://selectel.ru/services/cloud/storage/?section=prices
Yes | Yes | Yes | No | 9 | Digital assett manager (DAM) setup | 1 | 3 | 2 | 1
Yes | Yes | Yes | No | 10 | Okta integration DAM | 1 | 3 | 2 | 1
Yes | Yes | Yes | No | 11 | DAM enhancement: implement search by metadata in object storage, web-links creation for objects, user interface | 3 | 15 | 5 | 3 | To do research and gather more detailed functional requirements to find convenient open source project. Preliminary found list of suitable projects which can be used. Preliminary Estimation based on AWS JavaScript S3 Explorer. | https://github.com/awslabs/aws-js-s3-explorer/tree/v2-alpha | Functional requirements
Yes | Yes | Yes | No | 12 | Create API for DAM | 2 | 4 | 2 | 1
Yes | Yes | Yes | No | 13 | Interface DAM and Metabase to get links | 1 | 5 | 2 | 1 | REST requests (JSON)
Yes | Yes | Yes | No | 14 | Metabase report modification/creation | 1 | 4 | 1 | 1 | To include in report EDI links from S3 storage
Note on L9: Evgeniy Danilov: Скидка 5% - в калькуляторе не применена, возможно упростить billing - сделать плату только за гигабайты и траффик без запросов

## Functional requirements
№ | Функциональное требований для DAM (digital asset manager)
1 | WEB UI (доступ из браузера)
2 | Поиск по метаданным и просмотр содержимого хранилища
3 | Создание публичных ссылок с возможностью выгрузки
4 | Передача ссылок в Metabase
5 | OKTA-аутентификация

## Projects
https://github.com/cloudlena/s3manager
https://github.com/gaplo917/S3WebUploader
https://github.com/awslabs/aws-js-s3-explorer/tree/v2-alpha
https://github.com/teoadal/Storage
https://github.com/thobiast/s3_client/blob/master/s3_client/s3_client.py
https://github.com/aws/amazon-s3-encryption-client-java